## CR_Summary
Impacted Workstream | DEL | Demand # | DMND0000000
Impacted Report | - | Requested Date | 2020-07-01
Change Name | Provide ES Amount with NHI Price and Dealer Price
Change Description
Since BMS and Celgene have different criteria to measure ES amount, i.e. BMS uses Dealer price and Celgene uses NHI price, C-SCOR should provide two ES amount by providing choices to allow users to choose one of two criteria
Business Priority | High

## Requirement
# | Requirement ID | System | Report Name | Description
1 | DMND0000000_REQ_001 | C-SCAN |  | Recalculate hBMS ES Amount using NHI Price against both historical data and current month
2 | DMND0000000_REQ_002 | C-SCOR |  | Provide ES Actual, %P, %G and %E on NHI basis. Sope on which amount is calculated as NHI price basis is specified in Summary sheet
3 | DMND0000000_REQ_003 | C-STAR |  | Provide ES Actual, %P, %G and %E on NHI basis. Sope on which amount is calculated as NHI price basis is specified in Summary sheet
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40
41
42
43
44
45
46
47
48
49
50
51
52
53
54
55
56
57
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
106
107
108
109
110
111
112
113
114
115
116
117
118
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133

## Summary
| Approach アプローチ | 実現方法 How to achieve |  |  |  | Assumption 前提事項
Approach 1 | Calculate ES with Point-in-time NHI price from beginning | C-SCAN will look at BRIDGE price master (M_HIN_KAKAKU) |  |  |  | 1. Update historical ES Plan based on NHI price
(Raised by FFE) | 過去データ含めて当時の薬価で表示 | NHI price is identified with following conditions. |  |  |  | Planは過去データ含めて薬価ベースで再入力する
|  |  | 販売累積明細の発伝年月日（西暦）between 価格マスタの適用開始日 and 適用終了日 |  |  | 2. Historical EST will not be replaced with NHI based amount
|  |  | HATSUDEN_YMD in T_OROSHI_HANBAI_RUISEKI_MEISAI |  |  | ESTはそのまま使う（過去データでEST対比を見ないはず）
between TEKIYO_START_YMD and TEKIYO_END_YMD in M_HIN_KAKAKU
3. C-SCOR should show message to inform incosistent EST
4. Business and IT should discuss timing to replace PLAN in 2020
2020年のPlanの薬価置き換えのタイミングを今後検討する
5. No change required at C-SCOR front end design
Approach 1 - ES Ranking | Calculate with Point-in-time NHI price from 2021 | Same approach to identify NHI price from price master as Approach 1 |  |  |  | Same assumption as Approach 1 is applied
2021年以降のESを当時の薬価ベースで計算
Plus, note that 2020 ES Actual should be calculated based on NHI price
in order to calculate %G for 2021
Approach 2 | Calculate with latest NHI price from beginning | C-SCAN will look at BRIDGE price master (M_HIN_KAKAKU) |  |  |  | Change front end to hide Plan, EST, %P and %E
(Raised by FFE) | 過去データ含めて最新薬価で表示 | NHI price is identified with following conditions. |  |  |  | Plan、ESTとの対比は見せないよう既存レポートの変更を実施
価格マスタの適用開始日が最新のレコード
Use price entry which has latest TEKIYO_START_YMD in M_HIN_KAKAKU
Approach by Report
Application | Report | Appraoch 1 PIT NHI Price | Appraoch 2 Latest NHI Price | Appraoch 3 Dealer Price | Note
C-SCOR Dashboard | My Performance | Y |  |  | Actual Sales with PLAN and EST (Current and Previous month)
| My Geography | Y | Y |  | Monthly Trend with PLAN, EST and Previous Year (12 Months)
| Customer 360 Institution | Y | Y |  | Monthly Trend (12 Months) Only Actual
| My Customer Institution List | Y |  |  | Current month sales with previous month, previous year along with PLAN and EST
C-SCOR Drill Down | ES KPI | Y |  |  | Actual Sales with PLAN and EST (3 Years)
| ES Trend |  | Y |  | Daily Trend (2 Months), Only Actual
Monthly Trend for (3 Years), Only Actual
Quarterly and Half Trend (3 Years), Only Actual
Yearly Trend (3 Years), Only Actual
| ES Ranking | Y |  |  | Ranking by %P (2 Years)
| JD Net Detail | Y |  |  | ES Transaction (3 Months)
| JD Net Summary | Y |  |  | ES Transaction (3 Months)
C-STAR | Monthly ES | Y |  | Y | Actual Sales with BUDJET and PROJECTION
| ES Summary Table | Y |  | Y | Actual Sales with BUDJET, PROJECTION and PLAN
| ES Trend Daily | Y |  | Y | Actual Sales with BUDJET, PROJECTION and PLAN
| ES Trend Monthly | Y |  | Y | Actual Sales with BUDJET, PROJECTION and PLAN
| ES Alliance | Y |  | Y | Actual Sales with BUDJET and Alliance BUDGET
| ES Region District | Y |  | Y | Actual Sales with PLAN
| ES by Accounts (Top 300) | Y |  | Y | Ranking of Actual Sales by institution
| ES by Accounts (All) | Y |  | Y | Actual Sales by institution
| # of Accounts | Y
Input to C-SCAN
|  | 2020 |  | 2021 onwards
Data | Product | Dealer Price | NHI Price | Dealer Price | NHI Price
ES Actual | hBMS product | Y |  | Y | Y
| SP, EM, OP HL | Y |  |  | Y
| hCLG product |  | Y |  | Y
ES Plan | hBMS product | Y |  |  | Y
| SP,EM,OP HL | Y |  |  | Y
| hCLG product |  | Y |  | Y
ES EST | hBMS product | Y |  |  | Y
| SP,EM,OP HL | Y |  |  | Y
| hCLG product | - | - | - | -
ES Budget | hBMS product | Y |  |  | Y
SP,EM,OP HL
| hCLG product | - | - |  | Y
ES Projection | hBMS product | Y |  |  | Y
SP,EM,OP HL
| hCLG product | - | - |  | Y
Alliance Budget | hBMS product | Y |  |  | Y
SP,EM,OP HL
| hCLG product | - | - |  | Y
Note on A79: 作成者: Confirm with Akita-san if we are using this data

## My Geography, Custome 360
最新薬価
売上時薬価
Allow to choose either Point-in-time NHI Price(売上時薬価) or latest NHI Price(最新薬価)
最新薬価
売上時薬価
Allow to choose either Point-in-time NHI Price(売上時薬価) or latest NHI Price(最新薬価)

## ES Trend
Remove PLAN、EST、％P、%E
Calculate and display based on latest NHI Priace

## C-STAR
Dealer Price
NHI Price
Allow to choose either Point-in-time NHI Price or latest Dealer Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Hide in case of Dealer Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Hide in case of Dealer Price
Dealer Price
NHI Price
Dealer Price
NHI Price

## Indication Dropdowns (hidden)
Suggested dropdown list order:
ONC1 | IO LC
IO RCC
OP RCC
OPYV RCC
IO HN
ONC2 | IO GC
IO EC
IO CRC
| OP CRC | * according to OPYV CRC launch
| OPYV CRC | * according to OPYV CRC launch
IO MELA
OP MELA
OPYV MELA
ONC1,ONC2 | YV
IM | EQ
OR
HEMA | REV MM
REV FL
REV MDS
REV ATL
POM
SP
EM
IST
IO HL